# Memetics Research Bundle (FPF-based)

Version 0.1 | 2026-02-05 | Timezone: America/New_York

Purpose: a single, runnable artefact that bundles (1) context, (2) task definition, (3) work plan, and (4) a mechanism to run the work for multiple hours (and longer), using FPF conceptual forms.

Audience: Principal (you) + LLM agents (research, critique, synthesis) + any human reviewers.

FPF patterns explicitly used in this artefact (names as in FPF spec): NQD-CAL, E/E-LOG, BLP, SLL, Problem-CHR, MM-CHR, ADR patterns, and RoC-Autonomy Budget & Enforcement.

# Contents

1. Context

2. Task (Problem Frame + Acceptance)

3. Work Plan (multi-hour execution)

4. Long-Run Mechanism (governance + rhythm)

5. Artefacts & Templates (copy/paste)

6. References (primaries + access date)

# 1. Context

Memetics is the family of ideas that treats cultural information as a replicating, varying, and selected entity ("meme"), originally coined as an analogy to genes. The term was introduced to discuss why some cultural variants spread and persist, even when harmful to hosts.

In academia, "memetics" is controversial: many cultural evolution researchers argue that cultural inheritance does not require discrete gene-like units and that naive meme-analogies can mislead. Contemporary work often reframes the useful core as cultural evolution, social learning theory, and information diffusion, with clearer definitions and testable models.

This bundle sets up a research program that stays on the Pareto frontier between (a) conceptual clarity and (b) empirical tractability, while remaining useful for real-world analysis (e.g., online content diffusion, belief spread, institutional practices).

# 2. Task (Problem Frame + Acceptance)

## 2.1 Objective (one sentence)

Produce a defensible, testable research brief on memetics that (1) maps the concept space, (2) isolates the strongest operational definitions, (3) identifies 3-5 tractable research questions, and (4) proposes at least one empirical study design per question.

## 2.2 Scope

Included: origins of the meme concept; memetics vs cultural evolution; operationalizations (units, transmission, selection); measurement options; failure modes and critiques; practical applications (online diffusion).

Excluded: normative/political messaging tactics; instructions for manipulation; platform-specific abuse playbooks.

## 2.3 Acceptance criteria (Definition of Done)

At least 25 high-quality sources (books, peer-reviewed papers, reputable encyclopedias) with ISO dates and access date.

A concept map: definitions, competing schools, key objections, and what would falsify each claim.

A portfolio of 3-5 research questions on a Pareto frontier (novelty × feasibility × expected value).

For each question: a proposed dataset or data collection plan, a minimal analysis plan, and confounders/risks.

A 'valid-until' date for the brief + triggers for refresh (new datasets, new key papers, major platform changes).

## 2.4 Constraints

Timebox: 4–8 hours for v0.1 (single-day sprint).

Reproducibility: every factual claim must have a citation; every inference must be labeled as inference.

Multi-criteria thinking: avoid single-score rankings; keep a Pareto set when trade-offs remain.

Safety: no actionable guidance for targeted persuasion or coercion.

## 2.5 Primary outputs

Research brief (10–20 pages equivalent), plus an appendix with notes and extracted quotes (short excerpts only).

Bibliography database (CSV or Zotero export) with fields: citation, year, claim tags, quality rating, link, access date.

Decision log (ADR-style): definition choices, inclusion/exclusion rules, and why.

# 3. Work Plan (multi-hour execution)

The plan is written as a runbook: each phase has inputs, outputs, checks, and a stop condition.

## 3.1 Phase 0 — Setup (15–30 min)

Create a repo/folder with subfolders: /inputs, /notes, /citations, /drafts, /evidence, /logs.

Create three living documents: Problem Card, Characterization Passport, Decision Log (ADR).

Set autonomy and verification policy for LLM agents (see section 4.3).

## 3.2 Phase 1 — Rapid landscape scan (45–90 min)

Collect 10–15 seed sources: Dawkins origin, major memetics advocates, major critics, cultural evolution overviews.

Extract 1–2 sentence summaries + key definitions + 1 quote per source (≤25 words).

Build a first-pass taxonomy: units (what replicates), transmission (how), selection (why spreads), measurement (how observe).

## 3.3 Phase 2 — Operational definitions & falsifiability (60–120 min)

List candidate definitions of 'meme' (discrete unit, bundle, statistical regularity, graph motif, etc.).

For each definition, specify: observable proxy, measurement method, and at least one falsifying observation.

Record dominated definitions (worse on clarity and measurability) and keep the Pareto set.

## 3.4 Phase 3 — Research question portfolio (60–120 min)

Generate 15–25 candidate research questions (diversity-first).

Score each on three axes: Novelty (N), Quality/Use-value (Q), Diversity contribution (D). Do not aggregate into one number.

Select 3–5 non-dominated questions; keep 1–2 stepping-stone questions that open new measurement capabilities.

## 3.5 Phase 4 — Study designs (90–180 min)

For each chosen question, propose at least one empirical design: dataset, sampling, variables, analysis, and threats to validity.

Define minimum viable evidence: what result would increase confidence, and what would reduce it.

Write an Evidence Pack outline (what to capture so the work is auditable).

## 3.6 Phase 5 — Synthesis & publication surface (60–120 min)

Write the brief: definitions, debate map, question portfolio, proposed studies, limitations, and next actions.

Add 'valid-until' + refresh triggers.

Create a 1-page executive summary: what to believe, what not to believe, what to test next.

# 4. Long-Run Mechanism (governance + rhythm)

This section is the 'make it run for hours/weeks' mechanism: cadence, gates, budgets, and anti-drift controls.

## 4.1 Cadence (default)

Daily (or per session): 10 min plan -> 60–120 min focused work -> 10 min log + update 'next'.

Weekly: portfolio review (drop dominated items, add stepping stones, refresh 'valid-until').

Monthly: assumptions audit (what changed in the world? new papers? new data access?).

## 4.2 Roles (human + agents)

Principal (human): sets objectives, constraints, final selection policy.

Librarian agent: finds sources, extracts definitions/claims, maintains bibliography.

Skeptic agent: adversarially checks claims, looks for confounders, flags weak evidence.

Synthesizer agent: builds the concept map and writes the narrative, marking inference vs fact.

Method designer agent: turns questions into study designs and measurement plans.

## 4.3 Autonomy policy (levels + budgets)

Use a simple autonomy ladder (L0–L5 analogy): start at L1–L2 (drafting with mandatory review), then expand to L3–L4 only if the Evidence Pack and logs remain clean and error rates are low.

Budget autonomy as a resource: quota of tool calls, citations pulled, and 'risky actions' allowed per session. Any budget depletion triggers an escalation and a stop.

Critical gate: no new claims enter the brief without a citation or an explicit 'hypothesis' label.

## 4.4 Drift control (valid-until + refresh)

Every key decision (definition choice, inclusion rule, model choice) gets a 'valid-until' date.

When expired: Refresh (re-check), Deprecate (reduce status), or Waive (accept risk with explicit sign-off).

Keep an assumption ledger: if an assumption flips, re-run selection and update the brief.

## 4.5 Parity & reproducibility

Parity plan: fix comparison windows, budgets, datasets, and scoring rules before generating results.

Minimum two runs (or two seeds) for any stochastic step; record seeds/settings.

Publish a Pareto set when trade-offs remain; avoid collapsing to a single winner.

# 5. Artefacts & Templates (copy/paste)

## 5.1 Problem Card (FPF-style)

| Problem statement | One sentence: what is currently not possible, in this context. |
| --- | --- |
| Context / bounded scope | Where this applies; what is explicitly out of scope. |
| Signals / symptoms | What observations suggest the problem exists (data sources). |
| Acceptance criteria | What would count as 'solved' (thresholds, checks). |
| Constraints | Budget, safety, ethics, resources, reversibility. |
| Selection policy | How we choose among solutions (Pareto-only; tie-breakers). |
| Valid-until | Date + refresh triggers. |
| Owner | Role responsible for updates. |

## 5.2 Characterization Passport (what we measure and how)

| Compared objects | Which candidate definitions / models / study designs. |
| --- | --- |
| Viewpoints | Which stakeholders/roles and what they care about (rigor, utility, cost, safety). |
| Indicators (selected) | Explicit subset of measurable characteristics used for compare/accept. |
| Measurement templates | For each indicator: unit, polarity, method, dataset, cost. |
| Comparability rules | Same window/budget; normalization; handling missing data. |
| Evaluation protocol | Steps, repetitions, seeds; what counts as pass/fail. |
| Output format | Pareto set + notes on dominated options. |
| Assurance level | What evidence is required (citations, replications, audit). |
| Valid-until | Expiry date + triggers. |

## 5.3 Parity Plan (one-page reproducible comparison checklist)

| What is compared? | Candidates A/B/C, including versions. |
| --- | --- |
| Who compares? | Role; permissions; review responsibilities. |
| Budget envelope | Time, compute, number of sources, number of runs. |
| Data window | Dates covered; inclusion/exclusion rules. |
| Protocol version | Analysis pipeline version; tools; prompts. |
| Repetitions | Min 2; record seeds; report variance. |
| Indicators | Which measures matter; which are constraints vs objectives. |
| Selection rule | Pareto-only; tie-breakers (e.g., novelty, clarity). |
| What gets published? | Pareto set + rejected options with reasons. |
| Valid-until | Expiry date; when to rerun. |

## 5.4 ADR (Decision Log entry)

| Decision | What we chose (e.g., definition of meme, model class, dataset). |
| --- | --- |
| Alternatives | What we considered (with links to evidence). |
| Rationale | Why this dominates or is preferred on the frontier. |
| Evidence | Citations + any analyses; links to Evidence Pack. |
| Risks | What could make this wrong; failure modes. |
| Reversibility | Rollback plan; how to undo/change. |
| Assumptions | Key assumptions; what would flip the decision. |
| Valid-until | Expiry date + triggers. |
| Owner | Role responsible. |

## 5.5 Autonomy Budget Declaration (for LLM agents)

| Budget ID | Identifier to reference in logs. |
| --- | --- |
| Scope | Project, environment, and allowed tool domains. |
| Quotas | Max tool calls / max citations pulled / max tokens. |
| Risk bands | Low: auto; Medium: needs review; High: forbidden. |
| Resource caps | Time cap; parallelism; external calls. |
| Admissibility conditions | Prereqs: logging on, citation rules, sandbox only. |
| Override protocol | How to pause autonomy; who can resume. |
| Telemetry spec | What must be logged each step (actions, sources, deltas). |
| Depletion behavior | On quota exhaustion: stop + escalation + summary. |
| Valid-until | Expiry date; reauthorize rules. |

# 6. References (primaries + access date)

Access date for web sources: 2026-02-05

Dawkins, R. (2014-02-04). “What’s in a meme?” RichardDawkins.net. Accessed 2026-02-05.

Henrich, J., Boyd, R., & Richerson, P. J. (2002). “Five Misunderstandings about Cultural Evolution.” (working paper PDF). Accessed 2026-02-05.

Mesoudi, A. (2018). “Cultural Evolution.” Encyclopedia of Life Sciences (PDF). Accessed 2026-02-05.

Sutton, R. (2019-03-13). “The Bitter Lesson.” incompleteideas.net. Accessed 2026-02-05.

Mouret, J.-B., & Clune, J. (2015-04-20). “Illuminating search spaces by mapping elites.” arXiv:1504.04909. Accessed 2026-02-05.

SAE International (2021-05-02). “SAE Levels of Driving Automation refined for clarity…” sae.org blog post. Accessed 2026-02-05.

Ford, N., Parsons, R., Kua, P., & Sadalage, P. (2022). Building Evolutionary Architectures (2nd ed.). O’Reilly. (Reference for fitness functions and evolutionary architecture practices).